## Sheet1
Schedule
Week 1 | start building area
Week 2 | start building area
Week 3 | Decide on enemies to use/ finish building area
Week 4 | Figure out how to spawn enemies in waves | This might be the most
Week 5 | Figure out how to spawn enemies in waves/do it | difficult part of the project
Week 6 | Figure out how to spawn enemies in waves/do it | as far as implementing goes
Week 7 | Spring Break
Week 8 | Giving player points for their kills
Week 9 | Figuring out/implementing rules
Week 10 | Figuring out/implementing rules
Week 11 | Adding NPC as a shop using correct currency
Week 12 | Adding shop inventory/finishing week 11
Week 13 | Bug fixing/presentation
Week 14 | Bug fixing/presentation
Week 15 | Bug fixing/presentation
Grading Rubric
2 | location made, contains monsters
2.3 | location made, contains monsters minigame "starts"
2.7 | 2.3 reqs + points are awarded
3 | enemies spawn in waves
3.3 | points work for each wave, shop exists
3.7 | shop contains all items using correct currency
4 | Waves spawn, points awarded, point shop functional